## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
10.00%	Phase 1: / Programming	0.6%	$1,200	0.7%	$1,400	0.8%	$1,600	2.0 wks
20.00%	Phase 2: / Schematic Design	1.2%	$2,400	1.4%	$2,800	1.6%	$3,200	3.0 wks
15.00%	Phase 3: / Design Development	0.9%	$1,800	1.1%	$2,100	1.2%	$2,400	2.0 wks
30.00%	Phase 4: / Construction Documents	1.8%	$3,600	2.1%	$4,200	2.4%	$4,800	4.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	$600	0.4%	$700	0.4%	$800	1.0 wks
20.00%	Phase 6: / Construction Administration	1.2%	$2,400	1.4%	$2,800	1.6%	$3,200	n/a
100.00%	All Phases	6.0%	$12,000	7.0%	$14,000	8.0%	$16,000
Assuming a Construction Cost =							$200,000

## Hour Breakdown
Square Footage	23,000 SF
Estimated Dollar per Square Footage	50 $/SF
Total Estimated Construction Costs	$200,000.00
Architecture/Eng Fees - Percentage of Construction	6.0%
Architecture & Engineering Fees	$12,000.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	$1,200.00	$1,200.00	22 hrs	1.1 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks
Phase 2 - Schematic	20.00%	$2,400.00	$3,600.00	44 hrs	2.2 wks	1.5 wks	1.1 wks	0.7 wks	0.5 wks	0.4 wks	0.4 wks
Phase 3 - Design Development	15.00%	$1,800.00	$5,400.00	33 hrs	1.6 wks	1.1 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.3 wks
Phase 4 - Construction Documents	30.00%	$3,600.00	$9,000.00	65 hrs	3.3 wks	2.2 wks	1.6 wks	1.1 wks	0.8 wks	0.7 wks	0.5 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$600.00	$9,600.00	11 hrs	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	20.00%	$2,400.00	$12,000.00	44 hrs	2.2 wks	1.5 wks	1.1 wks	0.7 wks	0.5 wks	0.4 wks	0.4 wks
	100.00%	$12,000.00	$12,000.00	218 hrs	10.9 wks	7.3 wks	5.5 wks	3.6 wks	2.7 wks	2.2 wks	1.8 wks

## Hourly Rates
Skill Level	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs
OpeningDETAIL					6.0%
Skill Level 1 (Senior Architect)	$75/HR	$85/HR	$95/HR	40.0%
Skill Level 2 (Architect)	$55/HR	$65/HR	$75/HR	30.0%
Skill Level 3 (Intern)	$45/HR	$55/HR	$65/HR	30.0%
TOTAL				100.0%	6.0%